## Slide 2: Introducing the Annual Workplan
Purpose
Structure your events, projects and outreach activities
Transform association goals into actionable steps
Manage resources (time, volunteers, funds) effectively
Support associations to deliver an AGM and at least one activity per year by providing accountability
Value
Collaborative tool for leaders to plan association activities
Ensure all leaders are fulfilling their role and commitment to the association
Improve decision-making by committing to what is practical, reasonable and valuable to members
Align activities to the association vision and mission and contribute to achieving goals
Supporting resources
CSC Alumni Association Toolkit
2025 CSC Alumni Association Leaders Conference resources
Alumni Team and fellow association leaders

## Slide 3: Completing your annual workplan

## Slide 4: Overview
Annual workplan
Outline activities you intend to deliver up to 31 March 2027
You should focus on activities that will have the maximum benefit for members, are realistic to deliver within the current leadership, and support the association vision and mission
Include Annual General Meeting
Do not need to include Farewell and Welcome Home Events
Budget
Estimated and known costs for each activity
Funding is not guaranteed for all activities. Explore no and low-cost venues, existing activities that can bring alumni together
Agree how funds will be received and managed within the association leadership
You may wish to consider external funding and sponsorship- see the guidance on page 33 of the toolkit
Delivery plan
Planning tool to deliver agreed activities
Ensure workload and responsibilities are distributed across leadership
Plan activities across the year where possible

## Slide 5: Annual workplan
Month - in which the activity will be delivered
Date - the activity will be delivered (if known)
Activity title and description - provide a short, clear title for the activity and a brief description explaining what the activity involves.
Activity objectives - outline 3-5 clear and concise objectives of what the activity intends to achieve. Be specific and action and audience oriented, and identify intended impact.
Target audience - who is the activity for? Define the target audience (for example, new scholars, alumni, Distance Learners, local organisations, local communities). Where possible, provide an estimated audience size.

## Slide 6: Example
Month | Date | Activity title | Activity description | Objectives | Target audience
August | 3 events in different locations across August | A decade to change the world | This event will bring together Commonwealth Alumni who graduated between 2010-2020. Three events will be delivered in XX, XX and XX. Each will include 1 panel discussion (3 speakers + chair), a fireside chat (interviewer & interviewee), and a networking session (all attendees). Each event will be MC'd by an association leader, Alumni Advisory Panel member or key engaged association member. The panels will be subject/field specific and will be designed to showcase the contributions of each speaker to their field and sustainable development. The fireside chat will be with a notable or senior career alumnus from this decade who will deep dive into their contributions to sustainable and the impact of their Commonwealth Scholarship/Fellowship on their career and development trajectory. The event will close with a networking drinks reception for all attendees. The programme will be designed to enable to alumni to join the event at each of the 3 activity stages to encourage maximum attendance and flexible attendance. | 1. Showcase the work and contributions of Commonwealth Alumni from 2010-2020 to their subject/field and sustainble development. 2. Bring together this cohort to share memories of their time in the UK/studying via distance learning and reignite friendships and connections/ 3. Trial alumni engagement in new locations to connect with more/new members and support future activity planning | Alumni graduating between 2010-2020

## Slide 7: Annual workplan
Stakeholder engagement - list stakeholders and/or VIP guests (for example, British High Commission staff, Government Ministers).
Lead - confirm who in the alumni association leadership will be the main organiser and project manager for the activity.
Estimated budget - outline projected costs for the planned activities. Include estimated spend for events, communications, travel, resources, online platform, and any external services. When planning, consider both fixed and variable costs, as well as any potential income or funding sources.
Secretariat support - provide the details of any support you will require from the Secretariat to deliver your activity, for example sending email communications to scholars and alumni.

## Slide 8: Example
Stakeholder engagement | Lead | Estimated budget | Secretariat support required | Additional notes/comments
British High Commissioner /representatives Representatives of the national nominating agency |  | TBC: Venue hire Catering (light refreshments & drinks and canapes) IT/tech support Zoom license Badge labels Standing banner x3 | Subject/field breakdown of 2010-2020 graduates Send 2-3 event invitation emails and promote on CSC calendar and newsletters (where feasible) Provide breakdown of city location to support identification of potential event locations Invite BHC/representatives and members of the national nominating agency | Photography- alumni volunteers to take photos and share with association Need to explore free venues through alumni workplaces e.g. university campus spaces Standing banners will be retained and re-used for future events/activities

## Slide 9: Be creative and inclusive
Cohorts, subject experts, professional development and career needs/support, outreach activities, scholarship promotion
Appeal to different audiences- alumni and public
Coordinate with national/international events and celebrations
Celebrate achievements of alumni

## Slide 10: Completing your budget

## Slide 11: Considerations
CSC funding
Model of CSC funding not yet finalised
Options may include: ringfenced grant for each association; open competitive grant; combination of the two.
Payments will be made via International Bank Transfer.
Financial documents must be provided to CSC in advance of any payments.
External funding and sponsorship
This is at the discretion of each association.
Association leaders should read the guidance on pages 33-34 of the toolkit.
Inform the Alumni Team if you are seeking external funding and sponsorship for your association.
Membership fees
This is at the discretion of each association.
Must have robust financial management processes in place and designated role responsible.
Not all alumni will want to or can pay membership fees.
Need to outline a convincing and committed membership offer/benefits.

## Slide 12: Budget
Cost item - name of the item that requires payment, for example catering, venue hire.
Description/purpose - further details on the necessity of the cost item to support the event, or what the cost item entails. For example, for the cost item 'lunchtime refreshments', you may note buffet style refreshments, juice, and water.
Quantity - quantity of the cost item required, where necessary.
Unit cost - unit cost of the item required, where necessary.
Total cost & currency - total cost of the item, based on quantity and unit cost. In the column heading, state the currency the amounts are calculated in.
GBP cost - conversion of costs to GBP to ensure costs are within the allocated GBP budget.
Estimated cost (if actual not known) - in the early planning stages, you may wish to use this column to keep track of estimated costs whilst waiting for quotes.

## Slide 13: Example
Activity | Cost item | Description/ purpose | Quantity | Unit Cost | Total item cost (in local currency) | GBP cost | Estimated cost (if actual not known) | Notes
A decade to change the world- location XX | Venue | 1 room, theatre style seating for XX people; access to small room for refreshments and networking | 1 |  |  |  |  | 
A decade to change the world- location XX | Light refreshments | On arrival and break time (50 pax x2) Tea, coffee, water and 2x juice options Fruit | 100 |  |  |  |  | 
A decade to change the world- location XX | Networking refreshments | 5x choice of canapes 3x non alcoholic beverages Water | 50 |  |  |  |  | Food allergies/requirements to be collected at registration
A decade to change the world- location XX | IT support | Provide and set-up room tech incl. video screen and microphones (3x panel and 2x roaming) Ongoing tech support during the event | 1 |  |  |  |  | Check for Zoom and hybrid costs
A decade to change the world- location XX, XX, XX | Association branded banner | 3x association branded banners to display at front of room | 3 |  |  |  |  | 
A decade to change the world- location XX, XX, XX | Badge labels | Write-on labels for attendees | 150 |  |  |  |  | 
A decade to change the world- location XX, XX, XX | Pens | For attendee labels | 12 |  |  |  |  | Sign-in attendees on spreadsheet to save printing costs

## Slide 14: Resources
General planning information and guidance
Pages 16 - 17
Events and activities
Ensure events are accessible and inclusive for all scholars and alumni
Page 27
Inclusive Communities Policy
Activities should support your association vision and mission
Vision, mission and goals
Pages 33 - 34
Sponsorship and External Funding Principles
alumni@cscuk.org.uk
Alumni Team

## Slide 15: Questions?